## TO DO overview
Version: June 2020
START HERE: write the month and year of activity the red cell below. Excel will calculate the months in the TODO overview. These months are an indication of what to do when.
2020-12-01
OZSW Office tasks
Activity Organizer tasks
| 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01
DEVELOPING & ORGANIZING ACTIVITY
Send the proposal for the activity to the Section head (or discuss it in Section meeting)
Inform the OZSW about upcoming activity, if possible preliminary theme, title, program + dates
Send information package to organizer
Send out Save the Date (if desired)
Develop program and budget
Invite guest lecturers
Book lecture rooms and catering, also accommodation and flights for lecturers
Provide information, including budget, to the OZSW office, following the OZSW guidelines and formats/templates (see package information). This can be done in phases, with TBA / preliminary information
Make (preliminary) webpage and registration page
PROMOTION - WEBSITE + MAILINGLISTS
Send text for call for registrations
Send final information for webpage TBA's
Finish webpage (TBA's)
Send Call for Registration to OZSW and Filos-NL/Philos-L mailinglists, and announce on social media
REGISTRATION
Decide on which applicants are accepted and rejected
If applicable: Inform applicants about acceptance/rejection to the course.
Deadline registration and payment: 2 months before activity
Send final registrations with all personal details (e.g. dietary wishes) to organizer
Provide participants with any further details for preparation and participation
MONTH OF ACTIVITY TAKING PLACE
AFTER THE COURSE
Send the OZSW bills, and the budget sheet with income and expenses to OZSW
Send survey of the activity to participants (preferably on last day of activity)
Send survey results to organizer and section
Inform the OZSW office which of participants earned an ECTS certificate
Hand out ECTS certificates to those students who have met the course requirements